BITSAUTO

VoIP Monitoring Platform

Feature Implementation Time & Cost Estimate

Vol 1 — Vol 2 — Vol 3  ·  All 68 Features  ·  Days, Hours & USD Cost per Feature

──────────────────────────────────────────────────────────────────────────────────────────────────────────────

Report Date:  15 May 2026

Platform:  Sippy Softswitch / VoIP NOC Dashboard

Assumed Rate:  USD 500 / developer-day  (8 hours/day)  —  Senior Full-Stack Engineer

Cost Basis:  Solo developer; no infra cost — all processing runs on existing Replit deployment

Prepared by:  BitsAuto Engineering

Classification:  Internal — Confidential

──────────────────────────────────────────────────────────────────────────────────────────────────────────────

1.  Cost Assumptions & Rate Card

All estimates below are based on a single senior full-stack developer (TypeScript / React / Node.js / PostgreSQL / Sippy XML-RPC). Estimates assume: existing codebase familiarity, all patterns and shared infrastructure already in place (auth, DB, routing, Sippy integration), and no requirement for external API integrations unless explicitly noted.

| Parameter | Value | Notes |
| --- | --- | --- |
| Developer Daily Rate | USD 500 | Senior full-stack engineer; familiar with the BitsAuto codebase |
| Working Hours / Day | 8 hours | Focused development time, excluding meetings and review |
| Hourly Rate (derived) | USD 62 | $500 ÷ 8h |
| Infrastructure Cost | USD 0 additional | All features run on existing Replit deployment — no new servers, DBs, or services |
| Sippy API Dependency Risk | Low–Medium | Some features (codec, DTMF) depend on Sippy CDR field availability — verify before building |
| Estimate Confidence | ±20 % | Estimates include build + basic test; exclude QA cycles and user acceptance testing |
| Currency | USD | All costs quoted in US Dollars |

2.  Executive Cost Summary

High-level investment breakdown across all three volumes. Vol 1 shows historical effort already invested. Vol 2 and Vol 3 show forward-looking build cost for remaining and new features.

| Scope | Features | Status | Estimated Days | Estimated Hours | Estimated Cost (USD) |
| --- | --- | --- | --- | --- | --- |
| Vol 1 — Core Platform (all built) | 25 | Already Built | 111 days | 888h | $55,500 |
| Vol 2 — Already live (9 features) | 9 | Already Built | 52 days | 416h | $26,000 |
| Vol 2 — Remaining work (15 features) | 15 | Gap Only | 51 days | 408h | $25,500 |
| Vol 3 — New proposals (20 features) | 20 | Full Build | 131 days | 1048h | $65,500 |
| TOTAL — All 69 items | 69 | — | 345 days | 2760h | $172,500 |

Forward-Looking Investment (unbuilt work only)

To complete all remaining Vol 2 gaps (51 days) and build all 20 Vol 3 proposals (131 days):

| Work Package | Days | Hours | Cost (USD) |
| --- | --- | --- | --- |
| Vol 2 — Complete all remaining gaps | 51 | 408h | $25,500 |
| Vol 3 — Build all 20 new proposals | 131 | 1048h | $65,500 |
| TOTAL REMAINING INVESTMENT | 182 | 1456h | $91,000 |

3.  Volume 1 — Historical Effort Invested  (All 25 Features — 100 % Built)

All 25 Vol 1 features are live. The table below shows the estimated development effort invested to build each one. Rate: USD 500/day.

| Tier | Department | Feature | Status | Days | Hours | Cost (USD) | Build Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T1 | NOC & Operations | Live Call Quality Monitoring — MOS, Jitter, Latency, Packet Loss | Already Built | 7 | 56h | $3,500 | WebSocket push; per-call metrics DB; threshold alert triggers; real-time dashboard widget |
| T1 | Analytics | Call Session Tracking — CDR: ASR, ACD, PDD, CPS | Already Built | 5 | 40h | $2,500 | XML-RPC CDR fetch; KPI calculation engine; per-client aggregation; CPS from 1-hour window |
| T1 | Engineering | IP Endpoint Probe — TCP SIP port liveness check | Already Built | 3 | 24h | $1,500 | TCP probe scheduler; outage_log table; status badge on Server Monitoring page |
| T1 | Fraud & Security | Role-Based Access Control — Admin / Management / Viewer | Already Built | 4 | 32h | $2,000 | Replit OIDC integration; requireRole() middleware; 3-tier permission model; all routes gated |
| T1 | NOC & Operations | Alert Engine — threshold-based triggers + email delivery | Already Built | 6 | 48h | $3,000 | Gmail SMTP via Nodemailer; alert_rules table; cooldown logic; enable/disable per rule |
| T2 | Commercial & Client Management | KAM Management & Portfolio Assignment | Already Built | 8 | 64h | $4,000 | kams + kam_accounts tables; live call overlay; per-KAM BitsEye drill-down; portfolio cards |
| T2 | NOC & Operations | Traffic Drop Detector — >50 % drop alert | Already Built | 3 | 24h | $1,500 | Background 5-min job; 30-min cooldown; traffic_alerts table; open/resolved state machine |
| T2 | NOC & Operations | Client Traffic Pulse — per-client live concurrency cards | Already Built | 4 | 32h | $2,000 | Live call count; percentage-of-peak bar; trend indicator; Graphs page cards |
| T2 | Commercial & Client Management | Traffic Map — Leaflet choropleth by destination country | Already Built | 5 | 40h | $2,500 | CDR country field; TopoJSON world-atlas; violet colour scale; time-range selector |
| T2 | Finance & Billing | Revenue & Margin Analytics — 30-day P&L | Already Built | 6 | 48h | $3,000 | Admin 4-card view; KAM filtered-revenue mode; cost delta computation; chart overlays |
| T3 | Engineering | Sippy Change Watcher — IP rules, clients, vendors | Already Built | 5 | 40h | $2,500 | Polling + sippy_snapshots table; false-positive prevention; email notification per event |
| T3 | Fraud & Security | Security Hardening — Helmet.js, rate-limit, CSP | Already Built | 4 | 32h | $2,000 | 300/15min general; 20/15min auth; CSP headers; suspicious IP tracker with DB log |
| T3 | Fraud & Security | Fraud / FAS + IRSF Detection Engine | Already Built | 7 | 56h | $3,500 | Zero-billed, high-PDD, short-billed, early-answer categories; IRSF premium prefix scan |
| T3 | Engineering | Server Monitoring — 6-tab infrastructure view | Already Built | 6 | 48h | $3,000 | TCP probe; outage_log; RTP bandwidth chart; disk & memory metrics; SIP reg storm detection |
| T3 | Finance & Billing | Vendor Balance Tracker — delta-based cost calculation | Already Built | 4 | 32h | $2,000 | 2-hour rolling balance snapshots; cost = balance decrease over window; vendor cost cards |
| T4 | Finance & Billing | Rate Cards & Tariff Management | Already Built | 8 | 64h | $4,000 | Sippy tariff/rate CRUD; bulk import from CSV/XLSX; per-destination rate lookup |
| T4 | Engineering | DID Management | Already Built | 3 | 24h | $1,500 | List, assign, release DIDs via Sippy API; DID inventory page; bulk operations |
| T4 | Engineering | Multi-Switch Support | Already Built | 5 | 40h | $2,500 | SwitchesPanel in Settings; push rate changes to all enabled switches; per-switch status |
| T4 | Finance & Billing | Payments & Billing — full Sippy billing API | Already Built | 7 | 56h | $3,500 | Full coverage of Sippy billing API (articles 107440–107446); payment history; balance top-up |
| T4 | Engineering | Trunk & Trunk Connection Management | Already Built | 5 | 40h | $2,500 | Full CRUD for trunks and connections via Sippy XML-RPC; codec config; media relay |
| T5 | UX & Platform | Dark / Light Mode Toggle | Already Built | 2 | 16h | $1,000 | CSS variable system; ThemeProvider; localStorage persist; default dark on first load |
| T5 | UX & Platform | Quick Actions Command Bar — Ctrl+K / Cmd+K | Already Built | 3 | 24h | $1,500 | shadcn CommandDialog; role-filtered nav items; keyboard shortcut; sidebar hint text |
| T5 | Engineering | API Key Management | Already Built | 3 | 24h | $1,500 | vw_ prefix; SHA-256 hash storage; Bearer auth on /ext/ routes; instant revoke button |
| T5 | UX & Platform | Customizable Dashboard Widgets | Already Built | 4 | 32h | $2,000 | 5 toggleable sections; per-user preferences in DB; hidden-widget badge count |
| T5 | NOC & Operations | Mobile-Responsive NOC View | Already Built | 5 | 40h | $2,500 | Hamburger Sheet sidebar; responsive breakpoints; push notification opt-in in Settings |

Volume 1 Total:  122 developer-days  ·  976 hours  ·  $61,000  (historical investment already made)

4.  Volume 2 — Features Already Live  (9 of 24 — Historical Effort)

These 9 Vol 2 features are fully live. The table shows the estimated effort invested.

| Department | Feature | Status | Days | Hours | Cost (USD) | Build Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Finance & Billing | LCR Analyser | Already Built | 5 | 40h | $2,500 | /lcr-analyser; CDR vs all vendor rate cards; missed-savings table; per-route margin |
| Finance & Billing | Call Flow Simulator | Already Built | 6 | 48h | $3,000 | /call-flow-simulator; step-by-step dialplan trace; SIP routing logic without live call |
| Finance & Billing | Vendor SLA Scorecard | Already Built | 6 | 48h | $3,000 | /vendor-sla-scorecard; per-vendor ASR/ACD/PDD; SLA thresholds; breach highlighting |
| Finance & Billing | Cost Optimisation Engine | Already Built | 7 | 56h | $3,500 | /cost-optimisation; margin-per-route analysis; worst routes surfaced; improvement tips |
| Commercial & Client Management | Reseller White-Label Portal | Already Built | 8 | 64h | $4,000 | /reseller; scoped P&L; CDR reports; invoices per reseller; role-scoped data isolation |
| Commercial & Client Management | SLA Monitoring & Breach Alerting | Already Built | 6 | 48h | $3,000 | /sla-breaches; per-client SLA compliance tracking; auto breach email to KAM |
| Commercial & Client Management | Number Inventory Management | Already Built | 7 | 56h | $3,500 | /number-intelligence; range tracking; utilisation %; expiry alerting; porting tracker |
| Commercial & Client Management | Click-to-Call & Test Call Launcher | Already Built | 5 | 40h | $2,500 | /test-call; XML-RPC originate call; real-time progress tracking; CDR auto-linked |
| Engineering & Infrastructure | Multi-Switch Consolidated View | Already Built | 7 | 56h | $3,500 | /multi-switch; unified dashboard across all configured Sippy instances; per-switch KPIs |

Vol 2 Live Subtotal:  57 developer-days  ·  456 hours  ·  $28,500  (already invested)

5.  Volume 2 — Remaining Work to Complete  (15 Features)

The 15 items below are either fully unstarted (NOT BUILT) or have meaningful gaps (PARTIAL). "Days" represents the effort needed to fully complete each item from its current state.

| Department | Feature | Build Type | Days | Hours | Cost (USD) | Scope of Work |
| --- | --- | --- | --- | --- | --- | --- |
| NOC & Operations | Jitter & Packet Loss Monitor (complete gaps) | Gap Only | 2 | 16h | $1,000 | Add per-carrier trend chart on Graphs page + jitter column in Live Calls table. Core /rtp-analytics already live. |
| NOC & Operations | RTP Port & NAT Traversal Monitor (complete gaps) | Gap Only | 3 | 24h | $1,500 | Add one-way-audio detection grouped by subnet + inline STUN/TURN configuration hints. Base page live. |
| Analytics & BI | Peer Carrier Benchmarking (complete gaps) | Gap Only | 3 | 24h | $1,500 | Add industry-median comparison line + traffic-light indicator vs peers. /carrier-scoring already live. |
| Engineering & Infrastructure | Config Change Tracker (complete gaps) | Gap Only | 3 | 24h | $1,500 | Add visual diff viewer + rollback suggestion per config type. Sippy Change Watcher already live. |
| Engineering & Infrastructure | SIP Brute-Force Monitor (complete gaps) | Gap Only | 2 | 16h | $1,000 | Add auto-add-to-blocklist on >50 failed regs in 5 min + geo-origin map overlay. /firewall page live. |
| Fraud & Security | Fraud Velocity Scoring | Full Build | 6 | 48h | $3,000 | Multi-signal risk score 0–100 per account; velocity, CLI diversity, destination risk, time-of-day anomaly. New. |
| Fraud & Security | Robocall & Neighbour Spoofing Detector | Full Build | 5 | 40h | $2,500 | Sequential CLI detection + neighbour-spoofing flag + auto-block via XML-RPC. Extension of FAS engine. |
| Fraud & Security | Concurrent Call Limit Enforcer | Full Build | 3 | 24h | $1,500 | Poll live calls vs configured limit every 10s; alert + optional auto-disconnect; breach history log. |
| Analytics & BI | CDR Anomaly Detector — Statistical | Full Build | 6 | 48h | $3,000 | Nightly 3σ deviation job; anomaly inbox in Reports; severity score per batch; expected vs actual view. |
| Analytics & BI | Traffic Forecasting Dashboard | Full Build | 10 | 80h | $5,000 | Same-day-of-week 8-week model; hourly 24h forecast; confidence bands; >30 % deviation alert. |
| Analytics & BI | Geographic Revenue Heatmap | Full Build | 5 | 40h | $2,500 | World map with revenue/cost/margin/volume overlay; country drill-down; distinct from CDR traffic map. |
| Analytics & BI | Codec Negotiation Analytics | Full Build | 4 | 32h | $2,000 | Codec usage pie/bar chart; transcoding rate per carrier. Requires Sippy CDR codec field — verify first. |
| Engineering & Infrastructure | SIP Registration Database & Viewer | Full Build | 3 | 24h | $1,500 | Searchable real-time reg DB; username/IP/UA fields; unexpected-geography + UA flagging. |
| Engineering & Infrastructure | Maintenance Window Scheduler | Full Build | 2 | 16h | $1,000 | Recurring or one-off windows; alert suppression during window; NOC dashboard countdown banner. |
| Engineering & Infrastructure | DTMF Analytics & Failure Tracking | Full Build | 5 | 40h | $2,500 | DTMF method tracking per carrier; failure-rate score; cause-code flagging; trend chart. |

Vol 2 Remaining Subtotal:  62 developer-days  ·  496 hours  ·  $31,000

6.  Volume 3 — New Feature Proposals  (20 Features — Full Build Cost)

All 20 Vol 3 features are net-new — none have been started. Cost reflects a full build from scratch. Grouped by department.

NOC & Operations

| Feature | Business Value | Effort | Days | Hours | Cost (USD) | Scope & Notes |
| --- | --- | --- | --- | --- | --- | --- |
| AI-Powered NOC Assistant (LLM Chat) | Critical | High | 12 | 96h | $6,000 | LLM integration with read access to platform API; plain-English query interface; incident summaries; remediation suggestions. External LLM API cost separate (e.g. OpenAI ~$20–50/month usage). |

Finance & Billing

| Feature | Business Value | Effort | Days | Hours | Cost (USD) | Scope & Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Automated Invoice Delivery & Payment Collection | High | High | 8 | 64h | $4,000 | PDF invoice generation at billing cycle end; email with hosted payment link; paid/overdue/disputed tracking; auto balance lock on overdue threshold. |
| Carrier Invoice Reconciliation | Critical | High | 10 | 80h | $5,000 | Upload carrier PDF/CSV invoice; extract line items; cross-reference against BitsAuto CDRs; flag overbilled minutes, wrong rates, missing CDRs; generate dispute report. |
| Profit & Loss Forecasting | High | Medium | 6 | 48h | $3,000 | Next-month P&L projection using traffic trends, sell rates, buy rates; rate-renegotiation impact scenarios; QBR preparation dashboard. |
| Monthly Executive PDF Report | High | Medium | 5 | 40h | $2,500 | Auto-generated PDF on 1st of month; total minutes, revenue, gross margin, top 10 destinations, fraud count, carrier quality league table; configurable recipient list. |

Commercial & Client Management

| Feature | Business Value | Effort | Days | Hours | Cost (USD) | Scope & Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Client Self-Service Portal — White-Label | Critical | High | 14 | 112h | $7,000 | Fully white-labeled portal; client branding; own CDRs/balance/rate cards; top-up balance; download invoices; raise tickets. Separate auth scope. |
| Client Onboarding Kanban Tracker | Medium | Low | 4 | 32h | $2,000 | Kanban board: Draft → IPs Submitted → Provisioned → Test Call → Live; KAM assignment per card; blockers; last-action timestamp; linked to Wizard draft. |
| Predictive Client Churn Scoring | High | Medium | 7 | 56h | $3,500 | Daily churn risk score per client using CDR trend analysis; "At Risk" list on KAM dashboard; one-click outreach suggestion. |

Fraud & Security

| Feature | Business Value | Effort | Days | Hours | Cost (USD) | Scope & Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Zero-Trust Access Model | High | High | 10 | 80h | $5,000 | Every API call validated by role + registered device + IP range + time-of-day; admin actions from unrecognised IPs need secondary approval; IP-bound sessions. |
| Threat Intelligence Feed Integration | High | Medium | 6 | 48h | $3,000 | Subscribe to Spamhaus / ThreatCrowd feeds; real-time cross-reference of IPs and CLIs; auto-block VoIP fraud infrastructure IPs; daily threat feed refresh with email summary. |
| SOC 2 / ISO 27001 Compliance Checklist | Medium | High | 8 | 64h | $4,000 | Self-assessment checklist mapped to SOC 2 Type II controls; auto-evidence for verifiable controls; compliance readiness PDF export for auditors. |

Analytics & Business Intelligence

| Feature | Business Value | Effort | Days | Hours | Cost (USD) | Scope & Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Automated Route Optimisation Recommendations | High | Medium | 7 | 56h | $3,500 | Analyses routing priorities, carrier MOS/ASR trends, rate card margins; recommends carriers to de-prioritise, routes to renegotiate; estimated monthly savings; one-click apply option. |
| Regulatory Reporting — CALEA / GDPR | Medium | High | 8 | 64h | $4,000 | CALEA lawful intercept report in regulatory format; GDPR CDR anonymisation; right-to-erasure workflow; EU personal data residency controls. |
| Geographic Revenue Heatmap (Vol 3 Enhanced) | Medium | Medium | 5 | 40h | $2,500 | Enhanced Vol 2 #18 with per-carrier drill-down per country, QBR slide export, revenue-vs-cost margin overlay. Vol 2 base must be built first. |
| CDR Anomaly Detector (Vol 3 Advanced) | High | Medium | 7 | 56h | $3,500 | Builds on Vol 2 #20 with real-time (not just nightly) anomaly detection, ML-based pattern learning, and auto-alert to KAM on account-level anomaly. |

Engineering & Infrastructure

| Feature | Business Value | Effort | Days | Hours | Cost (USD) | Scope & Notes |
| --- | --- | --- | --- | --- | --- | --- |
| SBC / Firewall Rule Sync | High | Medium | 6 | 48h | $3,000 | Push approved IP to firewall via API (iptables / Cloudflare / FortiGate); audit trail of every rule push; one-click rollback. Integration cost varies by firewall type. |
| Configuration Backup & Point-in-Time Restore | High | Medium | 5 | 40h | $2,500 | Daily JSON snapshot of routing groups, rate cards, alert rules, IP rules; versioned storage; one-click restore; critical for disaster recovery. |
| Call Recording Management | Medium | Medium | 6 | 48h | $3,000 | Browse, search, stream call recordings from Sippy server via proxy; filter by account/date/destination/duration; bulk export ZIP; retention policy with auto-delete after N days. |
| Scheduled Bulk Actions | Medium | Low | 4 | 32h | $2,000 | Schedule one-off or recurring bulk operations with admin approval gates; "Block zero-traffic accounts every Sunday 02:00"; full before/after audit log. |
| CRM Integration — HubSpot / Salesforce | High | Medium | 7 | 56h | $3,500 | Sync client records; create Company in HubSpot on provisioning; CDR revenue updates CRM deal value; KAM assignment synced to CRM owner. |
| Webhook Push API for External Systems | High | Low | 4 | 32h | $2,000 | Outbound webhooks per event type: alert fired, fraud detected, balance low, client provisioned; HMAC-SHA256 signed payloads; retry with exponential back-off; delivery log. |

Vol 3 Total:  149 developer-days  ·  1192 hours  ·  $74,500

7.  Recommended Sprint Build Plan with Cost

The 35 remaining items (Vol 2 gaps + Vol 3 new) organised into 5 sprints in recommended build order. Cost per sprint assumes a single senior developer working full-time.

Sprint 1 — Highest ROI  (~5–6 weeks)

| Src | Department | Feature | Value | Effort | Days | Hours | Cost (USD) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vol 2 | NOC & Operations | Traffic Anomaly Detector (statistical baseline) | High | Medium | 7 | 56h | $3,500 | Extends Traffic Drop Detector; 14-day per-hour model; 2σ deviation alert |
| Vol 2 | Finance & Billing | Billing Report Generator — PDF / Excel | High | Medium | 5 | 40h | $2,500 | Closes manual invoice gap; PDF with company logo; Excel CDR attachment |
| Vol 2 | Fraud & Security | Fraud Velocity Scoring | Critical | Medium | 6 | 48h | $3,000 | Multi-signal 0–100 risk score; live NOC sidebar; account score history |
| Vol 2 | Fraud & Security | CDR Anomaly Detector (Statistical) | Critical | Medium | 6 | 48h | $3,000 | Nightly 3σ job; anomaly inbox; severity score per batch |
| Vol 3 | Finance & Billing | Carrier Invoice Reconciliation | Critical | High | 10 | 80h | $5,000 | Upload carrier invoice; cross-reference CDRs; auto dispute report |
| Vol 2 | UX & Platform | Scheduled Report Delivery | Critical | Low | 3 | 24h | $1,500 | Cron delivery of daily/weekly/monthly reports; builds on existing infra |
| Vol 2 | UX & Platform | Audit Log Viewer | Critical | Low | 3 | 24h | $1,500 | Tamper-evident admin action log; filterable table; CSV export |

Sprint 1 — Highest ROI  (~5–6 weeks) subtotal:  40 days  ·  320h  ·  $20,000

Sprint 2 — Revenue & Client  (~5–6 weeks)

| Src | Department | Feature | Value | Effort | Days | Hours | Cost (USD) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vol 2 | NOC & Operations | MOS Score Trending (historical) | High | Medium | 5 | 40h | $2,500 | MOS trend chart 24h/7d/30d; Quality Events log; Carrier Quality League Table |
| Vol 3 | Commercial & Client Management | Client Self-Service Portal | Critical | High | 14 | 112h | $7,000 | White-labeled portal; CDRs, balance, rate cards, invoices, ticket raising |
| Vol 3 | Finance & Billing | Monthly Executive PDF Report | High | Medium | 5 | 40h | $2,500 | Auto-generated PDF on 1st of month; revenue, margin, top destinations |
| Vol 3 | Finance & Billing | Automated Invoice Delivery & Payments | High | High | 8 | 64h | $4,000 | PDF invoice at billing cycle end; hosted payment link; overdue tracking |

Sprint 2 — Revenue & Client  (~5–6 weeks) subtotal:  32 days  ·  256h  ·  $16,000

Sprint 3 — Security & Integrations  (~4–5 weeks)

| Src | Department | Feature | Value | Effort | Days | Hours | Cost (USD) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vol 2 | Fraud & Security | Robocall & Neighbour Spoofing Detector | High | Medium | 5 | 40h | $2,500 | Sequential CLI + neighbour-spoofing + auto-block via XML-RPC |
| Vol 2 | Engineering | SIP Registration Database & Viewer | Medium | Low | 3 | 24h | $1,500 | Live reg list; username/IP/UA; unexpected-geography flag |
| Vol 3 | Engineering | SBC / Firewall Rule Sync | High | Medium | 6 | 48h | $3,000 | Push approved IP to firewall API; audit trail; one-click rollback |
| Vol 3 | Engineering | Webhook Push API | High | Low | 4 | 32h | $2,000 | Outbound webhooks per event type; HMAC-SHA256; retry logic; delivery log |
| Vol 3 | Engineering | Configuration Backup & Restore | High | Medium | 5 | 40h | $2,500 | Daily JSON snapshot; versioned storage; one-click restore |

Sprint 3 — Security & Integrations  (~4–5 weeks) subtotal:  23 days  ·  184h  ·  $11,500

Sprint 4 — Analytics & AI  (~5–6 weeks)

| Src | Department | Feature | Value | Effort | Days | Hours | Cost (USD) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vol 2 | Analytics | Geographic Revenue Heatmap | Medium | Medium | 5 | 40h | $2,500 | Revenue/cost/margin world map; country drill-down |
| Vol 2 | Analytics | Traffic Forecasting Dashboard | Medium | High | 10 | 80h | $5,000 | 8-week same-day model; hourly forecast; confidence bands |
| Vol 3 | NOC | AI NOC Assistant (LLM Chat) | High | High | 12 | 96h | $6,000 | Plain-English query interface; incident summaries; remediation suggestions |
| Vol 3 | Engineering | CRM Integration (HubSpot / Salesforce) | High | Medium | 7 | 56h | $3,500 | Sync client records; CDR revenue updates CRM deal value |
| Vol 3 | Finance | P&L Forecasting | High | Medium | 6 | 48h | $3,000 | Next-month P&L projection; rate-renegotiation impact scenarios |
| Vol 3 | Analytics | Auto Route Optimisation Recommendations | High | Medium | 7 | 56h | $3,500 | AI-driven carrier + route recommendations; estimated savings |

Sprint 4 — Analytics & AI  (~5–6 weeks) subtotal:  47 days  ·  376h  ·  $23,500

Sprint 5 — Hardening & Compliance  (~5–6 weeks)

| Src | Department | Feature | Value | Effort | Days | Hours | Cost (USD) | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vol 2 | Fraud | Concurrent Call Limit Enforcer | Medium | Low | 3 | 24h | $1,500 | Poll vs configured limit every 10s; alert + optional auto-disconnect |
| Vol 2 | Analytics | Codec Negotiation Analytics | Medium | Medium | 4 | 32h | $2,000 | Codec usage chart; transcoding rate per carrier. Verify Sippy field first. |
| Vol 2 | Engineering | Maintenance Window Scheduler | Low | Low | 2 | 16h | $1,000 | Alert suppression for planned downtime; NOC countdown banner |
| Vol 2 | Engineering | Two-Factor Authentication (TOTP) | Medium | Medium | 4 | 32h | $2,000 | Google Authenticator / Authy; QR enrollment; recovery codes; admin-enforceable |
| Vol 3 | Fraud | Zero-Trust Access Model | High | High | 10 | 80h | $5,000 | IP-bound sessions; device validation; secondary approval for admin actions |
| Vol 3 | Fraud | Threat Intelligence Feed Integration | High | Medium | 6 | 48h | $3,000 | Spamhaus / ThreatCrowd; real-time IP + CLI cross-reference; daily digest |
| Vol 3 | Fraud | Regulatory Reporting (CALEA / GDPR) | Medium | High | 8 | 64h | $4,000 | Lawful intercept report; GDPR anonymisation; right-to-erasure workflow |
| Vol 3 | Commercial | Predictive Client Churn Scoring | Medium | Medium | 7 | 56h | $3,500 | Daily churn risk score; "At Risk" KAM list; one-click outreach trigger |
| Vol 3 | Commercial | Client Onboarding Kanban Tracker | Medium | Low | 4 | 32h | $2,000 | Kanban pipeline: Draft → IPs → Provisioned → Live; linked to Wizard draft |
| Vol 3 | Engineering | Scheduled Bulk Actions | Low | Medium | 4 | 32h | $2,000 | Admin-approval-gated bulk operations; before/after audit log |
| Vol 3 | Engineering | Call Recording Management | Medium | Medium | 6 | 48h | $3,000 | Browse/stream/download recordings from Sippy; retention policy; bulk export ZIP |
| Vol 3 | Fraud | SOC 2 / ISO 27001 Compliance Checklist | Medium | High | 8 | 64h | $4,000 | SOC 2 control mapping; auto-evidence; compliance readiness PDF export |

Sprint 5 — Hardening & Compliance  (~5–6 weeks) subtotal:  66 days  ·  528h  ·  $33,000

8.  Grand Total Investment Summary

| Investment Category | Features | Developer Days | Hours | Cost (USD) | Notes |
| --- | --- | --- | --- | --- | --- |
| Vol 1 — Already built (historical) | 25 | 122 | 976h | $61,000 | Investment already made — platform is live |
| Vol 2 — 9 features already live (historical) | 9 | 57 | 456h | $28,500 | Investment already made — features are live |
| TOTAL ALREADY INVESTED | 34 | 179 | 1432h | $89,500 | Sunk cost — value already delivered |
| Vol 2 — Complete remaining 15 features | 15 | 62 | 496h | $31,000 | Forward investment required |
| Vol 3 — Build all 20 new proposals | 20 | 149 | 1192h | $74,500 | Forward investment required |
| TOTAL FORWARD INVESTMENT | 35 | 211 | 1688h | $105,500 | Full remaining build cost |
| GRAND TOTAL (all 69 items) | 69 | 390 | 3120h | $195,000 | Complete platform: Vol 1 + 2 + 3 |

──────────────────────────────────────────────────────────────────────────────────────────────────────────────

Infrastructure Note:  All features run on the existing Replit deployment. No additional hosting, database, or server costs are required for any feature listed above. The only potential third-party cost is for the AI NOC Assistant (LLM) — estimated at USD 20–100/month in OpenAI API usage depending on query volume.

──────────────────────────────────────────────────────────────────────────────────────────────────────────────

BitsAuto VoIP Monitoring Platform  ·  Feature Cost Estimate  ·  15 May 2026  ·  Rate: USD 500/day  ·  Confidential